## Web Project Plan
KRISTIN GOINS DIGITAL DESIGN · kristingoins.com · Marketing · Web Design · Strategy
Website Project Plan
A complete roadmap from kickoff to launch. Customize phases and timelines for each client project.
Phase | Task | Owner | Start Date | Due Date | Status | Deliverable | Dependent On | Notes
PHASE 1: DISCOVERY
PHASE 1 | Kickoff call — goals, audience, competitors | Kristin + Client | Week 1, Day 1 | Week 1, Day 1 | Complete | Meeting notes + brief | Signed proposal | 30-60 min call
PHASE 1 | Client intake form sent and completed | Client | Week 1, Day 1 | Week 1, Day 3 | Complete | Completed intake form | Kickoff call | Covers brand, tone, goals, audience
PHASE 1 | Content inventory — what client has vs. needs | Kristin | Week 1, Day 3 | Week 1, Day 5 | Complete | Content audit doc | Intake form | Includes photos, copy, logos
PHASE 1 | Competitor site review (3-5 sites) | Kristin | Week 1, Day 4 | Week 1, Day 5 | Complete | Competitor notes | Intake form | Note what's working and what isn't
PHASE 2: DESIGN
PHASE 2 | Sitemap / page structure approved | Kristin + Client | Week 2, Day 1 | Week 2, Day 2 | In Progress | Approved sitemap | Discovery complete | Get written sign-off
PHASE 2 | Wireframe / layout mockup built | Kristin | Week 2, Day 2 | Week 2, Day 4 | In Progress | Wireframe document | Approved sitemap | Shows section layout per page
PHASE 2 | Client wireframe review + approval | Client | Week 2, Day 4 | Week 2, Day 5 | Pending | Signed-off wireframe | Wireframe built | Max 2 revision rounds
PHASE 2 | Color, font, and brand direction confirmed | Kristin + Client | Week 2, Day 5 | Week 3, Day 1 | Pending | Style guide notes | Wireframe approval | Pull from existing brand or develop new
PHASE 3: BUILD
PHASE 3 | Platform set up (Squarespace/Wix) + domain connected | Kristin | Week 3, Day 1 | Week 3, Day 1 | Not started | Live staging site URL | Design approval | Client provides domain access
PHASE 3 | Homepage built and styled | Kristin | Week 3, Day 1 | Week 3, Day 3 | Not started | Staged homepage | Platform setup
PHASE 3 | All inner pages built | Kristin | Week 3, Day 3 | Week 4, Day 2 | Not started | All pages staged | Homepage approved
PHASE 3 | Copy added — client-provided or written by Kristin | Kristin / Client | Week 3, Day 3 | Week 4, Day 2 | Not started | Copy on all pages | Pages built
PHASE 3 | Images sourced, optimized, and uploaded | Kristin | Week 3, Day 4 | Week 4, Day 2 | Not started | All images live on site | Pages built | Compress all to <200KB
PHASE 3 | Contact form + lead capture set up + tested | Kristin | Week 4, Day 2 | Week 4, Day 3 | Not started | Working form confirmed | Pages built | Test on mobile too
PHASE 3 | Google Analytics connected | Kristin | Week 4, Day 3 | Week 4, Day 3 | Not started | GA4 tracking confirmed | Pages built
PHASE 4: QA & LAUNCH
PHASE 4 | Mobile responsiveness tested on 3+ devices | Kristin | Week 4, Day 3 | Week 4, Day 4 | Not started | QA checklist complete | Build complete | iOS, Android, tablet minimum
PHASE 4 | Page speed test — target 80+ on mobile | Kristin | Week 4, Day 4 | Week 4, Day 4 | Not started | GTmetrix/PageSpeed report | Build complete | Compress images if needed
PHASE 4 | SEO basics checked — titles, metas, H1s, alt text | Kristin | Week 4, Day 4 | Week 4, Day 5 | Not started | SEO audit checklist | Build complete
PHASE 4 | Client review round — feedback collected | Client | Week 4, Day 5 | Week 5, Day 2 | Not started | Revision notes | QA complete | Max 2 revision rounds per contract
PHASE 4 | Final revisions applied | Kristin | Week 5, Day 2 | Week 5, Day 3 | Not started | Updated site | Client review
PHASE 4 | Site published — domain pointed live | Kristin | Week 5, Day 3 | Week 5, Day 3 | Not started | Live URL | Final approval
PHASE 4 | Google Search Console submitted + sitemap live | Kristin | Week 5, Day 3 | Week 5, Day 4 | Not started | GSC verified + sitemap submitted | Site live
PHASE 4 | Client handoff + training walkthrough | Kristin + Client | Week 5, Day 4 | Week 5, Day 4 | Not started | Recorded walkthrough video | Site live | 30-min screen share
* Timeline assumes a 5-week build. Adjust for project scope. Starter = 2-3 weeks. Growth = 3-5 weeks. Pro = 5-7 weeks.
* Client delays (late content, late feedback) pause the timeline. Communicate this in your contract.